## Group Details
EPM 1173_4/Spring 2023
Group 7
Name | Student ID
Nikesh Pathak | c0906596
Maurvi Shah | c0897184
Pradip Shrestha | c0899894
Paulina Jaramillo | c0897079
Rojohn Shrestha | c0898077

## Task_Table
ID | Active | Task Mode | Name | Duration | Start | Finish | Predecessors | Outline Level | Notes
1 | Yes | Auto Scheduled | Collect RFP | 10 days | 2023 July 24 8:00 AM | 2023 August 04 5:00 PM |  | 1
2 | Yes | Auto Scheduled | Make RFP Available | 5 days | 2023 July 24 8:00 AM | 2023 July 28 5:00 PM |  | 2
3 | Yes | Auto Scheduled | Download RFP | 2 days | 2023 July 24 8:00 AM | 2023 July 25 5:00 PM |  | 3 | Download Fee Charge (Cost) - $10,000.00
4 | Yes | Auto Scheduled | Print RFP | 3 days | 2023 July 26 8:00 AM | 2023 July 28 5:00 PM | 3 | 3
5 | Yes | Auto Scheduled | Separate & Store | 5 days | 2023 July 31 8:00 AM | 2023 August 04 5:00 PM |  | 2
6 | Yes | Auto Scheduled | Segregate Technical & Financial Segments | 4 days | 2023 July 31 8:00 AM | 2023 August 03 5:00 PM | 4 | 3
7 | Yes | Auto Scheduled | Store in Separate Directories | 1 day | 2023 August 04 8:00 AM | 2023 August 04 5:00 PM | 6 | 3
8 | Yes | Auto Scheduled | Gather Technical Documentation | 25 days | 2023 August 07 8:00 AM | 2023 September 08 5:00 PM |  | 1
9 | Yes | Auto Scheduled | Prepare Technical Docs | 9 days | 2023 August 07 8:00 AM | 2023 August 17 5:00 PM |  | 2
10 | Yes | Auto Scheduled | Verify Technical Docs | 5 days | 2023 August 07 8:00 AM | 2023 August 11 5:00 PM | 7 | 3
11 | Yes | Auto Scheduled | Prepare Advisory Notes | 4 days | 2023 August 14 8:00 AM | 2023 August 17 5:00 PM | 10 | 3
12 | Yes | Auto Scheduled | Manage Technical Collection | 16 days | 2023 August 18 8:00 AM | 2023 September 08 5:00 PM |  | 2
13 | Yes | Auto Scheduled | Send to Technical Personnel | 1 day | 2023 August 18 8:00 AM | 2023 August 18 5:00 PM | 11 | 3
14 | Yes | Auto Scheduled | Meetings with Tech Dept | 10 days | 2023 August 21 8:00 AM | 2023 September 01 5:00 PM | 13 | 3
15 | Yes | Auto Scheduled | Compile & Submit Docs | 5 days | 2023 September 04 8:00 AM | 2023 September 08 5:00 PM | 14 | 3
16 | Yes | Auto Scheduled | Gather Financial Documentation | 27 days | 2023 August 07 8:00 AM | 2023 September 12 5:00 PM |  | 1
17 | Yes | Auto Scheduled | Prepare Financial Docs | 9 days | 2023 August 07 8:00 AM | 2023 August 17 5:00 PM |  | 2
18 | Yes | Auto Scheduled | Verify Financial Docs | 5 days | 2023 August 07 8:00 AM | 2023 August 11 5:00 PM | 7 | 3
19 | Yes | Auto Scheduled | Prepare Advisory Notes | 4 days | 2023 August 14 8:00 AM | 2023 August 17 5:00 PM | 18 | 3
20 | Yes | Auto Scheduled | Manage Financial Collection | 18 days | 2023 August 18 8:00 AM | 2023 September 12 5:00 PM |  | 2
21 | Yes | Auto Scheduled | Send to Financial Personnel | 1 day | 2023 August 18 8:00 AM | 2023 August 18 5:00 PM | 19 | 3
22 | Yes | Auto Scheduled | Meetings with Fin Dept | 12 days | 2023 August 21 8:00 AM | 2023 September 05 5:00 PM | 21 | 3
23 | Yes | Auto Scheduled | Compile & Submit Docs | 5 days | 2023 September 06 8:00 AM | 2023 September 12 5:00 PM | 22 | 3
24 | Yes | Auto Scheduled | Review Readiness | 0 days | 2023 July 22 8:00 AM | 2023 July 22 8:00 AM |  | 1
25 | Yes | Auto Scheduled | Ready and Send | 5 days | 2023 July 24 8:00 AM | 2023 July 28 5:00 PM |  | 1
26 | Yes | Auto Scheduled | Ready Documents | 5 days | 2023 July 24 8:00 AM | 2023 July 28 5:00 PM |  | 2
27 | Yes | Auto Scheduled | Bind Documents | 3 days | 2023 July 24 8:00 AM | 2023 July 26 5:00 PM | 24 | 3
28 | Yes | Auto Scheduled | Prepare separate packets | 2 days | 2023 July 27 8:00 AM | 2023 July 28 5:00 PM | 27 | 3
29 | Yes | Auto Scheduled | Prepare final package | 1 day | 2023 July 24 8:00 AM | 2023 July 24 5:00 PM |  | 3
30 | Yes | Auto Scheduled | Courier Document | 2 days | 2023 July 25 8:00 AM | 2023 July 26 5:00 PM |  | 2
31 | Yes | Auto Scheduled | Courier to Prospect | 1 day | 2023 July 25 8:00 AM | 2023 July 25 5:00 PM | 29 | 3 | Courier Expenses (Cost) – $300.00
32 | Yes | Auto Scheduled | Store Receipt | 1 day | 2023 July 26 8:00 AM | 2023 July 26 5:00 PM | 31 | 3

## Resource_Table
ID | Name | Initials | Type | Material Label | Group | Email Address | User Logon Account | Max Units | Standard Rate | Cost Per Use | Notes
1 | MarEx | M | Work |  |  |  |  | 100% | $18.00/h | 0
2 | PrintEx | P | Work |  |  |  |  | 100% | $15.00/h | 0
3 | Ana | A | Work |  |  |  |  | 100% | $16.00/h | 0
4 | BidMan-Tech | B | Work |  |  |  |  | 100% | $27.00/h | 0
5 | Marissa | M | Work |  |  |  |  | 100% | $20.00/h | 0
6 | BidMan-Fin | B | Work |  |  |  |  | 100% | $28.00/h | 0
7 | Alex | A | Work |  |  |  |  | 100% | $15.00/h | 0
8 | Tanya | T | Work |  |  |  |  | 100% | $20.00/h | 0
9 | Desjardine | D | Work |  |  |  |  | 100% | $15.00/h | 0
10 | Clark | C | Work |  |  |  |  | 100% | $15.00/h | 0
11 | Download Fee Charge | D | Cost | [6 empty] | 0
12 | Courier Expenses | C | Cost | [6 empty] | 0

## Assignment_Table
Task Name | Resource Name | % Work Complete | Work | Units
Download RFP | MarEx | 0 | 16h | 100%
Download RFP | Download Fee Charge | 0
Print RFP | PrintEx | 0 | 24h | 100%
Segregate Technical & Financial Segments | Ana | 0 | 32h | 100%
Store in Separate Directories | Ana | 0 | 8h | 100%
Verify Technical Docs | BidMan-Tech | 0 | 40h | 100%
Prepare Advisory Notes | BidMan-Tech | 0 | 32h | 100%
Send to Technical Personnel | BidMan-Fin | 0 | 8h | 100%
Meetings with Tech Dept | BidMan-Tech | 0 | 80h | 100%
Compile & Submit Docs | BidMan-Fin | 0 | 40h | 100%
Verify Financial Docs | Marissa | 0 | 40h | 100%
Prepare Advisory Notes | Marissa | 0 | 32h | 100%
Send to Financial Personnel | Alex | 0 | 8h | 100%
Meetings with Fin Dept | Marissa | 0 | 96h | 100%
Compile & Submit Docs | Alex | 0 | 40h | 100%
Bind Documents | Tanya | 0 | 24h | 100%
Prepare separate packets | Ana | 0 | 16h | 100%
Prepare final package | Ana | 0 | 8h | 100%
Courier to Prospect | Desjardine | 0 | 8h | 100%
Courier to Prospect | Courier Expenses | 0
Store Receipt | Clark | 0 | 8h | 100%